## Legend
TIQS Web Automation — Test Matrix
Legend
DONE (Green) | Automated case implemented in repo (web-automation branch)
Pending | Not implemented yet / Manual / Partial still open
Summary from Implementation Status column
DONE count | 53
Other rows | 139
File generated for Excel. Open sheet: TIQS Test Matrix

## TIQS Test Matrix
Sr No | Test Scenario | Test Cases | Test Steps | Data | Automated Status | Implementation Status | Comment
1. LOGIN - MOBILE NUMBER & OTP
1 | Login page UI | Verify login page loads correctly | Open TIQS login; check logo, heading, mobile, Get OTP, Create account, Sign in with User Id | URL: TIQS login | Automated | DONE (Green) | Positive
2 | Login page UI | Verify Get OTP disabled when mobile empty | Keep mobile empty; check Get OTP | blank | Automated | DONE (Green) | Negative
3 | Enter mobile | Verify login with valid mobile number | Enter 10 digit; Get OTP; OTP screen | 9812345678 | Automated | DONE (Green) | Positive
4 | Enter mobile | Verify Get OTP enabled only after 10 digits | 9 digits disabled; 10th enables | 9 then 10 digits | Automated | DONE (Green) | Edge case
5 | Enter mobile | Verify mobile field does not accept alphabets | Type letters | abcdefghij | Automated | DONE (Green) | Negative
6 | Enter mobile | Verify mobile field does not accept special characters | Type symbols | @#$%^&*()! | Automated | DONE (Green) | Negative
7 | Enter mobile | Verify mobile field keeps only first 10 digits | Type 12 digits | 981234567890 | Automated | DONE (Green) | Edge case
8 | Enter mobile | Verify <10 digits rejected | Enter 9 digits; Get OTP | 981234567 | Automated | DONE (Green) | Negative
9 | Enter mobile | Verify number starting with 3 rejected | Enter 3...; Get OTP | 3123456789 | Automated | DONE (Green) | Negative
10 | Enter mobile | Verify pasting mobile works | Paste 10 digits | 9812345678 | Automated | DONE (Green) | Edge case
11 | Enter mobile | Verify pasting with +91 or spaces | Paste +91 / spaces | +91 ... | Manual | Pending | Edge case
12 | Enter mobile | Verify unregistered mobile | Unregistered; Get OTP | 6000000000 | Manual | Pending | Negative
13 | Enter mobile | Verify blocked/inactive mobile | Blocked account; Get OTP | Blocked mobile | Manual | Pending | Negative
14 | Enter mobile | Verify Enter key submits mobile | Valid mobile; press Enter | 9812345678 | Automated | DONE (Green) | Usability
15 | Enter mobile | Verify Create account link | Click Create account | - | Automated | DONE (Green) | Positive
16 | Enter mobile | Verify Sign in with User Id link | Click Sign in with User Id | - | Automated | DONE (Green) | Positive
17 | Enter OTP | Verify OTP screen shows masked mobile | Check OTP screen text | +91 98****5678 | Automated | DONE (Green) | Positive
18 | Enter OTP | Verify login with valid OTP | Valid OTP; Proceed; PIN screen | Valid OTP | Partial | Pending | Positive
19 | Enter OTP | Verify invalid OTP shows error | Wrong OTP; Proceed | 123465 | Automated | DONE (Green) | Negative
20 | Enter OTP | Verify empty OTP cannot proceed | Blank OTP; Proceed | blank | Automated | DONE (Green) | Negative
21 | Enter OTP | Verify OTP with less digits | Short OTP; Proceed | 1234 | Automated | DONE (Green) | Negative
22 | Enter OTP | Verify OTP rejects letters/symbols | Type letters/symbols | ab12@# | Automated | DONE (Green) | Negative
23 | Enter OTP | Verify expired OTP rejected | Wait expiry; enter old OTP | Expired OTP | Manual | Pending | Negative
24 | Enter OTP | Verify Resend OTP works | Resend; use new OTP | - | Partial | Pending | Positive
25 | Enter OTP | Verify old OTP fails after Resend | Resend; enter old OTP | Old OTP | Manual | Pending | Negative
26 | Enter OTP | Verify Resend timer/limit | Resend many times | - | Manual | Pending | Edge case
27 | Enter OTP | Verify OTP attempt limit | Wrong OTP x5 | Wrong x5 | Manual | Pending | Security
28 | Enter OTP | Verify browser back from OTP | Back from OTP | - | Automated | Pending | Edge case
29 | Enter OTP | Verify page refresh on OTP screen | Refresh OTP page | - | Automated | DONE (Green) | Edge case
2. LOGIN - PIN
30 | Enter PIN | Verify PIN welcome message | Login till PIN; check greeting | Welcome back | Automated | DONE (Green) | Positive
31 | Enter PIN | Verify login with valid 4 digit PIN | Valid PIN; home loads | PIN test user | Automated | DONE (Green) | Positive
32 | Enter PIN | Verify wrong PIN shows error | Wrong PIN; Proceed | 0000 | Automated | DONE (Green) | Negative
33 | Enter PIN | Verify blank PIN cannot proceed | Empty PIN; Proceed | - | Automated | DONE (Green) | Negative
34 | Enter PIN | Verify PIN <4 digits | 3 digits; Proceed | 123 | Automated | DONE (Green) | Negative
35 | Enter PIN | Verify PIN accepts only digits | Letters/symbols | ab@# | Automated | DONE (Green) | Negative
36 | Enter PIN | Verify PIN is masked | Type PIN; check dots | 1234 | Automated | DONE (Green) | Security
37 | Enter PIN | Verify auto move to next PIN box | Type digit; cursor moves | - | Automated | DONE (Green) | Usability
38 | Enter PIN | Verify backspace to previous PIN box | 3 digits; backspace | - | Automated | DONE (Green) | Edge case
38b | Enter PIN | Verify MPIN complete navigates lobby without Proceed | Enter full MPIN; no Proceed click | - | Automated | Pending | Usability
39 | Enter PIN | Verify pasting PIN | Paste 4 digits first box | 1234 | Manual | Pending | Edge case
40 | Enter PIN | Verify PIN attempts limit | Wrong PIN x5 | Wrong x5 | Manual | Pending | Security
41 | Enter PIN | Verify Switch Account link | Switch Account → mobile | - | Automated | DONE (Green) | Positive
42 | Enter PIN | Verify Forgot PIN link | Forgot PIN → Set New PIN | - | Automated | DONE (Green) | Positive
43 | Forgot PIN | Verify set new PIN valid PAN | PAN + matching PIN | PAN/PIN | Partial | Pending | Positive
44 | Forgot PIN | Verify invalid PAN rejected | Wrong PAN format | 12345ABCDE | Automated | Pending | Negative
45 | Forgot PIN | Verify lowercase PAN | Type lowercase PAN | abcde1234f | Automated | Pending | Edge case
46 | Forgot PIN | Verify PAN of different user | Other user PAN | Other PAN | Manual | Pending | Security
47 | Forgot PIN | Verify PIN / Confirm mismatch | 1234 / 4321 | mismatch | Automated | Pending | Negative
48 | Forgot PIN | Verify weak PIN handled | 1111 / 1234 | weak | Manual | Pending | Security
49 | Forgot PIN | Verify all fields blank | Empty; Proceed | - | Automated | Pending | Negative
49b | Forgot PIN | Verify OTP/MPIN for new onboarding | New user journey | - | Manual | Pending | Positive
50 | Forgot PIN | Verify Switch Account on Set New PIN | Switch Account | - | Automated | Pending | Positive
157b | Enter PIN | Verify second browser login forces MPIN on first after refresh | Chrome lobby → Firefox same login → Chrome refresh | Same creds | Automated | DONE (Green) | Security / multi-device
3. HOME / DASHBOARD & LISTING
51 | Dashboard | Verify home page loads after login | Login; check watchlist/funds/holdings/positions/top stocks/quick trade/indices | Valid user | Automated | DONE (Green) | Positive
52 | Dashboard | Verify top bar NIFTY 50 and SENSEX | Check ticker | - | Automated | Pending | Positive
53 | Dashboard | Verify top menu navigation | Home/Orders/Holdings/Positions (+Funds/IPO/Research pending) | - | Automated | DONE (Green) | Positive
54 | Dashboard | Verify available funds and Add | Funds amount; Add click | - | Partial | DONE (Green) | Positive
55 | Dashboard | Verify Recently Viewed scroll till 10 | Open stocks; check list | - | Manual | Pending | Positive
56 | Dashboard | Verify Screeners cards + View All | Cards; View All | - | Automated | DONE (Green) | Positive
57 | Dashboard | Verify Today's Top Stocks tabs | Gainers/Volume/52W Low/High/Losers | - | Automated | DONE (Green) | Positive
58 | Dashboard | Verify quick trade chart/timeframes | Indices + 1D/5D/1M | - | Partial | Pending | Positive
59 | Dashboard | Verify indices section | Values/colours | - | Automated | DONE (Green) | Positive
60 | Dashboard | Verify empty state no data | New user | New user | Manual | Pending | Edge case
61 | Watchlist | Verify watchlist loads stocks/prices | Left panel | - | Automated | DONE (Green) | Positive
62 | Watchlist | Verify search in watchlist | Search RELIANCE | RELIANCE | Automated | DONE (Green) | Positive
63 | Watchlist | Verify search with no result | Search invalid | xyz123abc | Automated | DONE (Green) | Negative
64 | Watchlist | Verify switching tabs 1/2/3 | Click tabs | - | Automated | DONE (Green) | Positive
65 | Watchlist | Verify hover actions buy/sell/chart | Hover row | RELIANCE | Manual | Pending | Positive
66 | Watchlist | Verify price colours green/red/neutral | Watch live 1 min | - | Manual | Pending | Positive
67 | Screeners | Verify screeners listing page | View All; columns | - | Automated | Pending | Positive
68 | Screeners | Verify Back on screeners listing | Back button | - | Automated | Pending | Positive
69 | Early Signals | Verify Short/Mid/Long Term tabs | Tabs + counts | - | Automated | Pending | Positive
70 | Early Signals | Verify View More opens stock detail | View More | - | Automated | Pending | Positive
71 | Right panel | Verify Positions/Holdings mini panel | Home mini cards | - | Automated | DONE (Green) | Positive
4. POPUPS / TOAST
72 | Profile dropdown | Verify profile dropdown all options | See matrix | - | Automated | Pending
73 | Profile dropdown | Verify closes on outside click | See matrix | - | Automated | Pending
74 | Profile dropdown | Verify each option opens correct page | See matrix | - | Automated | Pending
75 | Logout | Verify logout works | See matrix | - | Automated | Pending
76 | Logout | Verify cannot go back after logout | See matrix | - | Automated | Pending
77 | Exit order | Verify Exit Order popup opens | See matrix | - | Automated | Pending
78 | Exit order | Verify Keep Order closes popup | See matrix | - | Automated | Pending
79 | Exit order | Verify Exit Order confirms | See matrix | - | Partial | Pending
80 | Exit order | Verify close X on popup | See matrix | - | Automated | Pending
81 | Exit order | Verify double click does not exit twice | See matrix | - | Manual | Pending
82 | Toast | Verify success toast add cash | See matrix | - | Partial | Pending
83 | Toast | Verify toast disappears automatically | See matrix | - | Automated | Pending
84 | Toast | Verify error toast on failure | See matrix | - | Manual | Pending
5. STOCK DETAIL
85 | Stock detail | Verify stock detail from watchlist | See matrix | - | Automated | Pending
86 | Stock detail | Verify Chart tab loads | See matrix | - | Automated | Pending
87 | Stock detail | Verify chart timeframe change | See matrix | - | Partial | Pending
88 | Stock detail | Verify Overview tab | See matrix | - | Automated | Pending
89 | Stock detail | Verify Fundamentals tab | See matrix | - | Automated | Pending
90 | Stock detail | Verify Technicals tab | See matrix | - | Automated | Pending
91 | Stock detail | Verify News tab | See matrix | - | Automated | Pending
92 | Stock detail | Verify tab switching keeps stock | See matrix | - | Automated | Pending
93 | Stock detail | Verify Buy opens order window | See matrix | - | Automated | Pending
94 | Stock detail | Verify Sell opens order window | See matrix | - | Automated | Pending
95 | Stock detail | Verify bookmark / add to watchlist | See matrix | - | Automated | Pending
96 | Stock detail | Verify stock with no news | See matrix | - | Manual | Pending
97 | Stock detail | Verify missing fundamentals | See matrix | - | Manual | Pending
98 | Stock detail | Verify large/negative numbers display | See matrix | - | Manual | Pending
99 | Stock detail | Verify market closed state | See matrix | - | Manual | Pending
6. ORDERS / HOLDINGS / POSITIONS
100 | Orders | Verify Open/Executed/Trades tabs | Click each tab | - | Automated | DONE (Green) | Positive
101 | Orders | Verify GTT tab | Click GTT | - | Automated | DONE (Green) | Positive
102 | Orders | Verify status labels | Complete/Rejected/Trigger Pending | - | Automated | Pending | Positive
103 | Orders | Verify order search | Search BHARTI | BHARTI | Automated | DONE (Green) | Positive
104 | Orders | Verify order search no match | Search zzzz | zzzz | Automated | DONE (Green) | Negative
105 | Orders | Verify Download button | Download file | - | Partial | Pending | Positive
106 | Orders | Verify empty orders state | New user | New user | Manual | Pending | Edge case
107 | Orders | Verify 3-dot menu options | Menu options | - | Automated | Pending | Positive
108 | Orders | Verify Repeat order | Repeat prefilled | - | Automated | Pending | Positive
109 | Orders | Verify Add to Watchlist from menu | Add to watchlist | - | Automated | Pending | Positive
110 | Holdings | Verify holdings summary | Invested/Current/Today/Overall P&L | - | Automated | DONE (Green) | Positive
111 | Holdings | Verify holdings list columns | Stock qty avg LTP value P&L | - | Automated | Pending | Positive
112 | Holdings | Verify P&L colours | Green/red | - | Automated | Pending | Positive
113 | Holdings | Verify P&L calculation | (LTP-avg)*qty | - | Partial | Pending | Positive
114 | Holdings | Verify holdings search | Search HDFC | HDFC | Automated | Pending | Positive
115 | Holdings | Verify Download in holdings | Download | - | Partial | Pending | Positive
116 | Holdings | Verify holdings row menu | 3-dot menu | - | Automated | Pending | Positive
117 | Positions | Verify positions summary | Booked/open/total P&L | - | Automated | DONE (Green) | Positive
118 | Positions | Verify Intraday/Delivery tags | Tags on rows | - | Automated | Pending | Positive
119 | Positions | Verify Exit on position | Exit + confirm | - | Partial | Pending | Positive
120 | Positions | Verify Convert/Add/Chart menu | Row menu | - | Automated | Pending | Positive
121 | Positions | Verify total row at bottom | Sum of rows | - | Automated | Pending | Positive
122 | Positions | Verify no positions state | New user | New user | Manual | Pending | Edge case
7. IPO
123 | IPO | Verify IPO tabs Open/Applied/Closed/Upcoming | See matrix | - | Automated | Pending
124 | IPO | Verify tab counts | See matrix | - | Automated | Pending
125 | IPO | Verify Open IPO list details | See matrix | - | Automated | Pending
126 | IPO | Verify Applied tab filters | See matrix | - | Automated | Pending
127 | IPO | Verify Closed tab | See matrix | - | Automated | Pending
128 | IPO | Verify Upcoming + Pre-apply | See matrix | - | Automated | Pending
129 | IPO | Verify IPO details popup | See matrix | - | Automated | Pending
130 | IPO | Verify IPO details popup close | See matrix | - | Automated | Pending
131 | IPO | Verify apply with valid UPI | See matrix | - | Partial | Pending
132 | IPO | Verify apply invalid UPI | See matrix | - | Manual | Pending
133 | IPO | Verify bid above cap | See matrix | - | Manual | Pending
134 | IPO | Verify bid qty above max | See matrix | - | Manual | Pending
135 | IPO | Verify insufficient funds | See matrix | - | Manual | Pending
136 | IPO | Verify apply closed IPO blocked | See matrix | - | Manual | Pending
137 | IPO | Verify duplicate application | See matrix | - | Manual | Pending
138 | IPO | Verify Refresh button | See matrix | - | Automated | Pending
139 | IPO | Verify no IPO state | See matrix | - | Manual | Pending
8. RESPONSIVENESS
140 | Responsive | Desktop 1920x1080 | See matrix | - | Partial | Pending
141 | Responsive | Laptop 1366x768 | See matrix | - | Partial | Pending
142 | Responsive | Tablet | See matrix | - | Partial | Pending
143 | Responsive | Mobile | See matrix | - | Partial | Pending
144 | Responsive | Zoom 50-150% | See matrix | - | Manual | Pending
145 | Responsive | Login small screen | See matrix | - | Partial | Pending
146 | Responsive | Wide tables scroll | See matrix | - | Manual | Pending
147 | Responsive | Portrait/landscape | See matrix | - | Manual | Pending
9. CROSS BROWSER
148 | Cross browser | Login Chrome | See matrix | - | Partial | Pending
149 | Cross browser | Login Firefox | See matrix | - | Partial | Pending
150 | Cross browser | Login Safari | See matrix | - | Manual | Pending
151 | Cross browser | Login Edge | See matrix | - | Partial | Pending
152 | Cross browser | Fonts/colours/charts match | See matrix | - | Manual | Pending
153 | Cross browser | Mobile browsers | See matrix | - | Manual | Pending
154 | Cross browser | Older browser versions | See matrix | - | Manual | Pending
10. SECURITY & AUTHENTICATION
155 | Authentication | Verify pages cannot open without login | Holdings URL after logout | - | Automated | Pending | Security
156 | Authentication | Verify session timeout | Idle then click | - | Manual | Pending | Security
157 | Authentication | Verify same account login on two devices | Chrome then Firefox; Chrome refresh → MPIN | Same creds | Automated | DONE (Green) | Business rule
158 | Authentication | Verify session after close/reopen | Close browser; reopen | - | Manual | Pending | Edge case
159 | Authentication | Verify tampered token rejected | Change token; refresh | - | Manual | Pending | Security
160 | Security | Verify SQL injection rejected | SQL in fields | OR 1=1 -- | Manual | Pending | Negative
161 | Security | Verify XSS in search not executed | script tag | <script> | Automated | Pending | Negative
162 | Security | Verify site uses HTTPS | Check HTTPS | - | Automated | DONE (Green) | Security
163 | Security | Verify PIN/OTP not in URL/logs/network | Network tab | - | Manual | Pending | Security
164 | Security | Verify autocomplete off for PIN/OTP | Browser suggestions | - | Manual | Pending | Security
165 | Security | Verify cannot see other user data by id | Change API id | - | Manual | Pending | Security
166 | Security | Verify Get OTP rate limit | Call repeatedly | - | Manual | Pending | Security
11. LOAD / PERFORMANCE
167 | Load | Home page load <3s | See matrix | - | Automated | Pending
168 | Load | 100 users login | See matrix | - | Automated | Pending
169 | Load | 1000 users market open | See matrix | - | Automated | Pending
170 | Load | Watchlist under load | See matrix | - | Manual | Pending
171 | Load | 200 holdings load | See matrix | - | Manual | Pending
172 | Load | Memory leak 1 hour | See matrix | - | Manual | Pending
173 | Load | Stock chart load <3s | See matrix | - | Automated | Pending
12. NETWORK ERROR
174 | Network | Internet off during login | See matrix | - | Manual | Pending
175 | Network | Internet off on OTP | See matrix | - | Manual | Pending
176 | Network | Internet lost on home | See matrix | - | Manual | Pending
177 | Network | Internet comes back | See matrix | - | Manual | Pending
178 | Network | Slow 3G | See matrix | - | Manual | Pending
179 | Network | Server 500 handling | See matrix | - | Partial | Pending
180 | Network | API timeout | See matrix | - | Partial | Pending
181 | Network | Order with network drop | See matrix | - | Manual | Pending
182 | Network | Page 404 | See matrix | - | Automated | Pending
13. GENERAL / UI
183 | UI | Verify no spelling mistakes | Read screens | - | Manual | Pending | UI
184 | UI | Verify SEBI/NSE/BSE footer | Login footer | - | Automated | DONE (Green) | UI
185 | UI | Verify Terms and Privacy links | Click both | - | Automated | DONE (Green) | Positive
186 | UI | Verify Play/App Store / QR | Click icons | - | Automated | DONE (Green) | Positive
187 | UI | Verify Tab key order on forms | Tab on login | - | Manual | Pending | Accessibility
188 | UI | Verify refresh keeps user logged in | Refresh home | - | Automated | Pending | Positive
189 | UI | Verify multiple tabs | Logout one tab | - | Manual | Pending | Edge case